## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | 79 | Simulate a 30 audio car sales journey to analyze the Falcon S2 buying process. | MUST HAVE | 5 | Varshitha | 3- Completed
2 | 2 | 79 | Converted 30 audio sales journey into text format | MUST HAVE | 4 | Varshitha | 3- Completed
3 | 3 | 79 | Conversion of live speech recording to text format | MUST HAVE | 5 | Varshitha | 3- Completed
4 | 4 | 79 | Identification of only customer sentences from the audio file and analyze the sentiment,intent and entite's for each customer sentence in the conversation | MUST HAVE | 5 | Varshitha | 3- Completed
5 | 5 | 79 | Analysing the sentiment, intent and entites along with ai sugesstiond for each customer sentence from the audio file and as well as the recording. | MUST HAVE | 4 | Varshitha | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 1279 | Collection of 30 datasets & text conversion | 2025-10-16 | 2025-11-04 | Varshitha | Build | 3- Completed | 10
79 | 1279 | Conversion of live speech to text | 2025-11-12 | 2025-11-22 | Varshitha | Coding | 3- Completed | 8
79 | 1279 | Sentiment analysis for the customer sentences of audio files and as well as live speech | 2025-11-25 | 2025-12-02 | Varshitha | Integration Test | 3- Completed | 10
79 | 1279 | AI suggestions for the live speech customer sentences | 2025-12-06 | 2025-12-11 | Varshitha | Integration Test | 3- Completed | 11

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
M-1 | 2025-11-04 | Presented Milestone1 tasks | Started filling form today
M-2 | 2025-11-12 | Understand the process of implementing milestone2 | Started working on milestone2
M-2 | 2025-11-13 | Installing the software that are required for the task | working on it
M-2 | 2025-11-17 | Implementing the code for the milestone2 | Implemented
M-2 | 2025-11-19 | Identified Errors | Working of bugs
M-2 | 2025-11-20 | Completed the task | Rectified the bugs
M-2 | 2025-11-22 | Presented Milestone2 | Updated all the agile documents
M-3 | 2025-11-25 | Undestand how to work on milestone3 | Started implimenting
M-3 | 2025-11-26 | Developing the code for milestone3 | work in progress
M-3 | 2025-12-27 | Dicussed about the output | Tried to modify the functionality
M-3 | 2025-12-01 | Presented the milestone3 | Updated all the sheets
M-4 | 2025-12-07 | Discussed about the task of milestone4 | Started working on it
M-4 | 2025-12-08

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-10-16 | 2025-11-04 | Muktineni Varshitha |  | Yes
2 | 2 | 2025-11-12 | 2025-11-22 | Muktineni Varshitha |  | Yes
3 | 3 | 2025-11-25 | 2025-12-02 | Muktineni Varshitha |  | Yes
4 | 4 | 2025-12-06 | 2025-12-11 | Muktineni Varshitha |  | Yes