## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Muktineni Varshitha | 2025-11-04 | Generated a code for converting audio files to text | Milestone1 | Muktineni Varshitha | Logical | Corrected it | 04/11/1025 | Closed | nil
2 | Muktineni Varshitha | 2025-11-22 | Generated a code for Recording live speech data and converting live speech to text | Milestone2 | Muktineni Varshitha | User Interface | Corrected it | 2025-11-22 | Closed
3 | Muktineni Varshitha | 2025-12-02 | Generated a code for analysing sentiment, intent and entite for customer speech | Milestone3 | Muktineni Varshitha | Standards |  | 2025-12-02 | Closed
4 | Muktineni Varshitha | 2025-12-11 | Generated a code for AI Sugesstion along with sentiment,intent and entite analysis for both audio uploading and live speech recognation | Milestone4 | Muktineni Varshitha | Standards |  | 2025-12-11 | closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others